## QI Action Points
2026 Quarter I CMT-Project Teams Meeting Action Points
Meeting Date | Project Team | Action Points | Responsible Person(s) | Due Date | Status by Q2 | Comments / Updates
16th April | PROSPER | Expedite signing of the land agreement for the irrigation experimental sites incorporating management input and consultation with DRC on a template | Omar | 30th June | In Progress | At the stage of review with MO and the Legal officer.
|  | Expedite establishment of costs for procuring FFS training manuals/charts | CO | 20th April | Completed | Field delivery to be done by 17th July 2026
|  | Share final copy of the FFS training manual for input by Nester before printing | Omar | 31st May | Completed
|  | Establish a budget for procuring sand and cement for installing the rainfall measurement equipment procured | MEALO/PO-Livelihood | 31st May | In Progress | Costs to be covered from the savings
|  | Verify total savings for the period, budget gaps and place a request for reallocation early enough | Project Accountant | 30th April | In Progress | Pending report approval by MCC
|  | Ensure clarity in statement of variance reasons | Project Accountant | Continuous | In Progress | Adopted in the Q2 review
|  | Overspends should be minimized and well documented | Project Accountant | Continuous | In Progress | Adopted in the Q2 review
|  | Check the practice of reporting same figs in the budget and accountability for items that may not have fixed rates | Project Accountant | Continuous | In Progress | Adopted in the Q2 review
|  | Strengthen budget monitoring practice and communicate Savings figures to staff on a monthly basis | Project Accountant | Continuous | In Progress | Continous guidance needed for the Accountant
|  | Write to MCC to follow up on approval of 3 pending critical activities | MP | 30th April | Completed
|  | Write to MCC about the balance of funds not yet received for the period | CF | 30th April | Completed
|  | Place formal inquiry for a sufficient office space | Omar | 30th June | Not started | Jackson and Omar to engage OPM
|  | Level group expectations continuously | Omar | On-going |  | Continous
|  | Improve quality of the group experimental plots including the size of Plots and application of the good agronomic practices | Omar | TBD |  | Continous
|  | Organize stakeholder reports and share accordingly | Omar | 30th June | Not started | Herbert to support Omar and share
20th April | WASER | Consult on the accommodation options in BidiBidi to enable staff relocate closer to the office location | PC | 24th April | In progess | Six months' support was received from WVU for 03 rooms. However, the staff were uncomfortable because of the distances.
|  | Pre-qualify missing service providers in Yumbe – including Stationery and negotiation with Escape Village | Proc. Officer | 31st May | Not started | Procurement to undertake their own selection process.
|  | Timely communicate emergency plans to Procurement | POs | Continuous |  | Largely dependent on AVSI short notice engagements.
|  | Request AVSI to formally communicate key changes to the project design that have a bearing on the partnership agreement e.g., Household targets | PC | 30th April | Completed | Meetings with AVSI resolved the household number discrepancies; WVU took on the additional HHs
|  | Write a formal letter to the key stakeholders to communicate exit from Loli | PC | 24th April | Not started | Not submitted; but verbal discussions done
|  | Investigate the complaint about 8 H/Hs not existing in the targeted village and sub county | PC | 24th April | Completed
|  | Submit project files to key stakeholder offices | PC | 24th April | Not started | Files noted submiited
|  | Develop a clear template for Management Financial reporting | CF | 21st April | Completed
|  | Conclude the NSSF no. issue for the remaining 3 staff | Project Accountant | 31st May | In Progress | Concluded for 2 staff, 1 CBT has not submitted. In the reporting, the Accountant needs to include committed
|  | Hold meeting between CF and Project A/c to harmonize unclear budget and accountability issues | Project Accountant | 30th April | Completed | A checklist provided by AVSI. Budget issue cleared; however, intrnal accountabilities still a la
20th April | SRILL | Expedite the recruitment of an Agronomist to support project activities on ground | PC (with support of HR office) | 30th April | Completed
|  | Develop & share a catchup plan for implementation of the outstanding activities | PC | 23rd April | Completed
|  | Update the stakeholder files with the new project information | PO | 24th April | In progress | Pending submission of reports
|  | Ensure timely submission of Bi-monthly reports to the funding partner | PC | Continuous |  | Continous
20th April | Organic Cereal #8 | Finalize contract with the CBF to support implementation | PC (with support of HR office) | 24th April | Completed
|  | Avail an easily accessible account to the groups | CF | 22nd April | Not started | An account to be created by 31st August
|  | Organize project information and share with key stakeholders | PC | 30th April | Completed
|  | Fast track delayed activity payments and ensure timely payments going forward | Project Accountant | Continuous | In Progress | Timely payments except in June
|  | Consolidate the balances of funds on completed activities & identify areas of re-allocation | Project Accountant | 30th April | Completed | Areas of savings identified
|  | Strengthen coordination between programs and finance | PC/Accountant | Continuous | In Progress | Improvement noted however, meetings are recommended
21st April | HESI | Meet to discuss reallocation of the savings | Project Accountant | 22/4/2026 | Completed | Reallocations to be used for repair of the shallow well
|  | Develop the final workplan for the project | MEALO | 22/4/2026 | Completed
|  | Complete activity reports and file – livelihood | PO/PA - Omar/Fazira | 5th May | In Progress | Pending reviews by MEALO
|  | Complete activity reports and file – health | PO - Laura | 5th May | In Progress | Pending reviews by MEALO
|  | Share Q3 report and Q1 plan with key stakeholders | PA | 30th May, | Not started | To be prioritised
|  | Establish survival rate of woodlots | MEALO | 30th May | Completed | 58%
|  | Share sample of action plans drawn for learning visit to agro-forestry sites & most cohesive groups | PO - Omar | 30th April | In Progress | Some actions require continous support
21st April | MPT | Write to MO regarding management support in securing staff accommodation | PO - Omar | 22nd April |  | Six months' support was received from WVU for 03 rooms. However, the staff were uncomfortable because of the distances.
21st April | INSPIRE | Liaise with Omar to provide details of staff who need accommodation | Team Leader | 21st April | Completed
|  | Write about the accommodation issue to the contacts provided | MO | 21st April | Completed | IRC provided 7 rooms for 6 months
|  | Confirm availability of budget for Imvepi Office support under the different projects hosted there | Team Leader | 30th April | In Progress | Further consultations with PROSPER and Operations on cost sharing
|  | Ensure timely submission of all reports to the funding partner | Team Leader | Continuous | In Progress | Timely submissions, however, require quality assurance
|  | Strengthen collaboration between the Finance, Procurement and Programs for timely procurement of items, payment of service providers and acountability | Team Leader/Accountant | Continuous |  | Documents are getting misplaced in the procurement office.
|  | Improve cohesion among team members including project support staff | Team Leader | 30th June & beyond | In Progress | Revolving funds introduced to enhance cohesion.
22nd April | I-UPSHIFT | Schedule a meeting btn ED and the Resource person identified | SOC | 22nd April | Completed
|  | Develop and adhere to a plan for supporting the project | SDO | 27th April | Not started | Need to harmonise with INSPIRE PL
|  | Uphold mentorship schedule of twice a week to improve performance of the groups | SDO | Continuous | In Progress | Started by the new support staff
|  | Proritise on Marketing and Financial Literacy trainings during the mentorship | SDO | On-going | Completed
|  | Share quarterly work plan – complete activities by May | SDO | 24th April | Completed
|  | Strengthen coordination between Finance, procurement and Programs – for effective Financial reporting | PO/Accountant | Continuous | In Progress | Advised to adhere to the weekly meetings.
|  | Conduct bi-weekly meetings; Fridays 9:00 am – 10:30 am and update the time on google calender | SDO | 22nd April | In Progress | Inconsitent meetings
|  | Issue a contract to the mentor that will be engaged | SOC | TBD | Completed
|  | Investigate the reason for attrition rates among the PWD; any linkages (of the attrition rates) to specific enterprises and emerging trends in the outcome harvesting tool/mentorship tool online | MEALC | 12th June | Completed
|  | Reflect deeper on the possibility of using competition to motivate the groups further | MEALC/PC | TBD | Not started | Referred to CMT for further discussion
|  | Closely monitor gps that demonstrated no progress financially/non-financially | PO/SDO | May - June | In Progress | Weaker groups prioritised
|  | Improve timeliness of online payment approvals | Account signatories | Continuous | In Progress | Accountant advised to be flexible
23rd April | RCCV-EBA | Use speaking photos with clear captions in presentation | PO | Continuous | In Progress | Adopted in the Q2 review
|  | Complete all project activities by June | PO | 30th June |  | Project extended to October
|  | Pay courtesy visit and deliver workplan for the extension period to the key stakeholders | PO (Hillary) | 29th April | Completed
|  | Improve the statement of outcomes in the presentation with support of the MEAL staff – integrate with outcome harvesting activity | PO | May - June | Not started | MEAL to support the PO
|  | Organize a database for the tree farmers | PO | 31st May | Not started | MEAL to support the PO
|  | Locate the lists for items distributed in the project | PO | 4th May | In Progress | Efforts didnot yield much results
|  | Hold Bi-weekly team meetings; Fridays 2:00 pm – starting 8th May | PO | Continuous |  | Inconsitent meetings
|  | Consider direct discussion with DFOs regarding future procurement opportunities | Procurement Officer | TBD | Completed
|  | Obtain evidence from Mahad regarding communication to the Private Nursery Operators the DFO Arua district provided and engage her accordingly | PO (Hillary) |  |  | No evidence during the meeting
|  | Improve the statement of the lessons learnt – and share the presentations | PO | 28th April | Not started | MEAL to support the PO
|  | Share a copy of the activity report written (for activities reported done) | PO | 27th April | In Progress | Reports in the file but incomplete
|  | CF and Hillary to meet and clarify on the 36M reported already spent on the 10ha restoration activity before its completion/achievement of targets | CF & PO (Hillary) | 30th April | Completed
|  | Adhere to the internal financial management practices | CF | Continuous | In Progress
23rd April | SEA-WNK | Prepare CNs in the first month of the quarter | POs | Continuous | In Progress | Inconsistence in sharing the CNs as agreed
|  | Undertake adequate consultations before writing CNs to improve quality of the CNs submitted for review/approval | POs | Continuous | In Progress | Activities discussed during weekly meetings
|  | Develop a catch plan incorporating all the activities | CPC | 24th April | Completed | Not implemented
|  | Discuss activities into detail during the PMU and weekly team meetings for clarity and shared understanding | CPC/CPM | Continuous | In Progress
|  | Refer the challenge regarding the Toll-Free line procurement to the Legal Officer with support of the CPM | Procurement Officer | 30th April | In Progress | Planned maintenance by 27th July 2026
|  | Reach out to Program Managers of FOZ and SPACE regarding review of the technical proposals for the MTE | CPM | 24th April | Completed | Multiple channels to be used for future engagements
|  | Organize a team level meeting to honestly discuss and address the recurring slow project implementation | CPM | 27th April | Completed | Meeting done but slow implementation remains
|  | CPM and CPC to meet and further reflect on the project implementation and restrategize to improve performance | CPM | 15th May | Completed | Advised to sort the indifferences
|  | Submit the past quarter’s report and new quarterly plan | CPM | 8th May | Completed
|  | Start participating in sector Working Group meetings under Rhino Camp Refugee Settlement | PO Madi Okollo | Immediately | In Progress
RISK and Compliance
23rd April | N/A | Focus on key risk and compliance issues for management attention in the presentation | ARCO | Continuous | In Progress | Adopted in Q2 review
|  | Formally request for audit documents relevant for ARCO from the Head of Finance | ARCO | Continuous | In Progress
|  | Meet with ED to discuss access to MoUs by ARCO | ARCO | 24th April | Completed | Process for new MoUs initiated
|  | Conduct Q1 internal audit | ARCO | 15th May | Not started | Further discussion with MO on the standards for an internal audit
|  | Forward the Safeguarding concerns raised by UCCM to ARCO | SOC | 23rd April | Completed
|  | Conduct HR and Program Audits; Bi-annually in June and Nov | ARCO | June & Nov. | Not started | Guidance needed fom HR office
|  | Schedule meetings with respective Officers to fill the risk matrix | ARCO | 27th - 28th April | In Progress | Advise to adopt physical visits, one-on-one meet ups
|  | Intentionally budget for risk and compliance costs in proposals | ARCO | Continuous | Not started | Advised to include spot checks as activities
|  | Prioritize review of the draft Risk and Compliance policy | CMT | June | Not started
|  | Draft guidelines for Risk & Compliance implementation – 3rd week of May | ARCO | 23rd May | In Progress | Pending adoption
|  | Pronounce the SMT during the next staff meeting | ED | 5th May | Not started | Prioritised for Mid Year Meeting

## Q2 Action Points
2026 Q2 Management and Project Teams Meetings Action Points
Project/Unit | Action Points | Responsible Person | Due Date | Status by Q3 | Comments/Remarks
WASER | Orient the CBTs and Roosters on organisation culture and values | HR Office | 31st July 2026 | In Progress
| Project Coordinator and Accountant to meet with ED on the financial status | Vincent | 21st July 2026 | Delayed/Off Track
| Roosters to be paid using the balance on the Stipends for the CBTs | Harriet | Continous | Deferred/Cancelled
| Develop a specific procurement plan for RICE West Nile infromed by the contract | Susan | 17th July 2026 | Completed
| Communicate to AVSI on the use of ofifcial communication channels | Vincent | Immediate | Completed
| Document issues regarding Modus Operandi that need the ED to engage with AVSI | Vincent | Immediate | Completed
| Adopt a presentation format that can be easily understoood explaining tagrtes and variances | Vincent | Continous | Completed
| Pre-qualify missing service providers in Yumbe | Susan | TBD | Completed
| Establish the number of staff under WASER that still need accomodation in the base camp so that MO notifies World Vision | Vincent | 17th July 2026 | Completed
| Submit Project files to the key stakeholders | Francis, Richard | 31st July 2026 | Completed
| Back the verbal commication to stakeholder about withdrawl from Loli with a formal letter | Francis, Richard | 31st July 2026 | Completed
EELAG | Realign the file of the Agronomist to support other Agrirelated projects | HR Office | 31st July 2026 | Delayed/Off Track
| Share Procurement request for selection of an institution for the ASKNETs | Patrick | 17th July 2026 | Delayed/Off Track
| Update stakeholder files with information on the extension phase | Patrick | 17th July 2026 | Delayed/Off Track
| Develop a profile for the water for production sites to ascertain their functionality | Patrick and Joel | 24th July 2025 | Delayed/Off Track
| Share wallets and support documens for all activtiies completed | Patrick | Immediate | Delayed/Off Track
| Properly document shifting of activities in the proejct workplan | Vincent | Continous | Delayed/Off Track
| Develop a catch up and follow closely | Vincent | 31st July 2026 | Delayed/Off Track
| Share financial information and BVAs during project meetings | Belinda | Continous | Delayed/Off Track
Organic Cereal #8 | Generate a plan for using the savings that can address exsiting gaps in the project | Nichodemus | 23rd July 2026 | In Progress
| Do gap filling for the farmer fields that are affected by the dry spell | Vincent | 24th July 2026 | In Progress
| Document why male farmers adopt GAPs faster or more than female farmers | Richard | 31st July 2026 | In Progress
| Document success and change stories emerginf from the project | Herbert | TBD | In Progress
| Develop a standard for Agric farming that can be rolled out to other projects | Joel and Richard | 30th August 2026 | In Progress
i-UPSHIFT | Recruit a staff to support the extention phase of the project | HR Office | 31st July 2026 | In Progress
| Develop a plan to support the groups based on the gaps identified | Faidah | 17th July 2026 | In Progress
| Make all the groups from Cohort 2 to sign commitment funds for utilisation of the funds | Faidah | 31st July 2026 | In Progress
| Coordinate weekly project team meetings to reflect and refine | Micheal | Continous | In Progress
| Develop a plan to follow up groups or members that have moved to other locations | Faidah | 31st July 2026 | In Progress
| Document the status of all the groups, including active memberships, innovation stage, earnings etc | Faidah | 21st July 2026 | In Progress
| Discuss in the project team meeting how the groups can be motivated | Rolex | 22nd July 2026 | In Progress
| Adjust the Q2 financial report based on the addendum signed | Micheal | 14th July 2026 | In Progress
| CMT to give direction on the pre financing arrangement to be used for activity implementation | Liberia | TBD | In Progress
| Clear pending payment for Service providers and stakeholders | Micheal | Immediate | In Progress
| Plan to complete the documentation of the 6 groups that were absent | Veronicah | 24th July 2026 | In Progress
| Finance to participate in monitoring visit so as to support in record keeping as well as value for money assessment | Micheal | Continous | In Progress
| Follow up with ILO on the disbursement of funds | Micheal | 14th July 2026 | In Progress
| Generate a means of centrally managing fuel as opposed to activity based | Micheal | Continous | In Progress
RCCV-EbA | Deliver start up kits to the livelihood groups and the model farmers | Sabir | 31st July 2026 | In Progress
| Complete the restoration of the 22.7 hectares of the forest land | Sabir | 1st August 2026 | In Progress
| Update the project files in the offices of the CAO, LCV, RDC, RCC | Hillary | 14th July 2026 | In Progress
| Conduct an outcome harvest to investigate the outcomes reported | Denis | 31st July 2026 | In Progress
| Complete the data entry into the database for all the participants and conclude this with a data audit | Denis | 30th August 2026 | In Progress
| Generate an outcome journal for the project ready to be shared when requested | Denis | 31st July 2026 | In Progress
| Map all the trees planted and generate a visual board or inforgraphical representation | Hillary | TBD | In Progress
| Ascertain the survival rate for all the trees planted since the start of the project | Hillary | 30th August 2026 | In Progress
| Hold Bi-weekly project team meetings; Fridays 2:00 pm | Sabir | Continous | In Progress
| Trace the project participants, their location, income status, etc | Sabir | 31st July 2026 | In Progress
Resource Mobilisation | Develop and keep an updated tracker for MoUs of the organisation | Francis | 24th July 2026 | In Progress
| Review the RM strategy to suit to the current trends of resoruce mobilisaion | Francis | TBD | In Progress
| Identify alternative RM ventures and advise the Management | Francis | 31st July 2026 | In Progress
| Develop capacity statements for all the Program Areas so that they are accessible during resource mobilisation | Francis | 30th August 2026 | In Progress
| Organise feedback sessions after feedback has been received from a potential donor | Francis | Continous | In Progress
| Aggregate the expected funds from the concepts and proposals submitted | Francis | Continous | In Progress
In Progress
HESI | Complete the repair and relocation of the shall well using the savings and reallocation | Omar and Fazira | 30th Sep 2026 | In Progress
| Support in weekly supervision of the repair process of the well until complete | Omar | Continous | In Progress
| Prepare Q3 report, and workplan and update the stakeholder files | Herbert | 31st July 2026 | In Progress
| Brief the Agronomist on supporting Fazira while on leave and other technical aspects of the project | Vincent | 15th July 2026 | In Progress
| Adopt quarterly reporting and workplanning that is aligned to the organisation culture | Herbert | Continous | In Progress
| Complete the installation of the sign posts for project visibility | Omar and Fazira | 24th July 2026 | In Progress
| Profile the water for production sites including the volume of water produced, number of participants accessing, use etc. | Omar and Fazira | 30th Oct 2026 | In Progress
| Develop a lesson learnt booklet including the success factor that can be shared with donors, social media etc | Herbert | TBD | In Progress
| Follow up with Northern Umbrella on the connection of the water to support the farmer groups | Omar | 24th July 2026 | In Progress
PROSPER | Finalise the review and roll out the land agreement form | Omar | 16th July 2026 | In Progress
| Ensure the landlords and groups sign the land agreements for all land used for and by the project participants | Omar | 30th August 2026 | In Progress
| Print additional manuals and distribute to the respective users | Omar | 17th July 2026 | In Progress
| Accountant to meet ED on the 5% co funding by the organisation | Lydia | Immediate | In Progress
| Complete the project baseline survey and ensure the findings are used to improve implementation | Herbert | 31st July 2026 | In Progress
| Engage other DLG officials (political, admnistrative) in the irrigation site establishment process | Omar | Continous | In Progress
| Develop a grant disburement guideline to be used during the block grants | Omar | 31st July 2026 | In Progress
| Submit June project report to the MEAL Officer for review | Omar | 31st July 2026 | In Progress
| Identify areas for capacity development and share with MCC | Herbert | 22nd July 2026 | In Progress
| Idenfiy Indicatorsa that are challenging to measure, propose alternatives and share with MCC | Herbert | 31st August 2026 | In Progress
| Conduct appraisal for CBTs | Omar | 20th July 2026 | In Progress
| Replace the CBT | Omar | 31st July 2026 | In Progress
| Allocate a laptop for the Gender Officer | Lydia | 20th July 2026 | In Progress
NB: Request for Motorcycle by the MEAL Officer
TASO - Malaria Response | Write a formal letter to the DHO on the presentation of the resolution as a bylaw | Mayega with support of the Legal officer | 28th July 2026 | In Progress
| Follow up with Assets team to provide furniture for the PO based in Terego | Consolate | 16th July 2026 | In Progress
| Participate in health sector coordination meetings with immediate effect | Consolate | Continous | In Progress
| Engage the health lead partner so as to incorporate the efforts of the project in the reports | Consolate | 31st July 2026 | In Progress
| Include the Name of the organisation in the Wallet activity narrations | All Project Officers | Continous | In Progress
| Include explanatory notes for the financial presentation where variances exit | Gloria | Continous | In Progress
| Follow up on the pending payment for the computer components to be procured | Gloria | 16th July 2026 | In Progress
| Share information on the malaria trends in the quarterly news letter | Denis | Continous | In Progress
| Team challenged to work and corporate with other projects, tasks etc. | Team | Continous | In Progress
Ebola Response - AWO | Revise the programmatic presentation to elimate the metrics that account for the average number of activities implemented | Denis | 17th July 2026 | In Progress
| Strengthen the linkage between the schools and health facilities on ebola alert reporting | James | Continous | In Progress
| Develop a mechanism for tracking the events conducted by the health clubs in the schools | Denis | 20th July 2026 | In Progress
Risk and Compliance | Isolate compliance issues needed for management attention and share | Patrick | 24th July 2026 | In Progress
| Timely share issues specific to deparments or projects for action | Patrick | Continous | In Progress
| Hold an advosory meeting with ED, MO and CF to discuss the way forward with the internal audit | Patrick | 31st July 2026 | In Progress
| Complete the risk matrix for the organisation through a consultative process | Patrick | 30th Aug 2026 | In Progress
| Generate a risk color code for RICE West Nile risk classification but align with the standard codes | Patrick | 30th Aug 2026 | In Progress
| Conduct a HR audit with the support of the Human Resoruce office | Patrick | 30th Oct 2026 | In Progress
| Convene the CMT to review the draft risk and compliance policy | Patrick | 30th Sep 206 | In Progress
| Convene a team to review the risk and compliance implementation guidelines | Patrick | 30th Aug 2026 | In Progress
INSPIRE | Introduce a document for receiving and dispatching documents from the procurement office | Suzan | TBD | In Progress
| Further consultation with PROSPER and Operations team on the logistics of Imvepi Office | Mildred | 24th July 2026 | In Progress
| Refine success stories to address the quality assurance gaps | Rodgers | 24th July 2026 | In Progress
| Refine the report presented to capture the accurate proejct status and share back with the Management | Mildred | 24th July 2026 | In Progress
| Project teams to visit the ED's office for one on one discussions | Project Team | Immediate | In Progress
| Project team to offer rotational security checks on weekends for the assets in the field office | Project Team | Continous | In Progress
| Develop a catchup plan for the project and share with management | Mildred | 29th July 2026 | In Progress
SEA WNK | Plan activities jointly with the District Natural Resource Office for ownership and proper scheduleling | Clere and Hillary | Continous | In Progress
| Discuss the feedback on the CNs reviewed with the Project Officers | Sadam | Continous | In Progress
| Designate etkeast two days in the week for review and approval of concept notes | Sadam and Jackson | Continous | In Progress
| Start tracking activities using an activty tracker that clearly stipulates the timelines, completion status etc | Sadam | 31st July 2026 | In Progress
| Escalate non reponsiveness of the partners to the ED for action | Jackson | Continous | In Progress
| Engage the service provider to fix the toll free and generate options of call forwarding so that it can be received from home when the attendant is away | Suzan | 24th July 2026 | In Progress
| Prioritise procurement processes for the project like any other project | Suzan | Continous | In Progress
| Provide timely implementation update on Whatsaap and in person to the CPM, MP, ECT | Hillary, Sadam and Clere | Continous | In Progress
| Uniform planning and implementation of project activities in Madi Okollo and Obongi | Clere and Hillary | Continous | In Progress
| Develop strategies to complete the review and development of the regulatory frameworks | Sadam and Jackson | 28th July 2026 | In Progress
| Procurement and Finance team to meet to discuss the steaky issues | Jeraldyn | 28th July 2026 | In Progress
| Management to write a memo on the use of other cars for project work | Belinda | 20th July 2026 | In Progress
| Strengthen budget monitoring through the monthly BVAs in the project team meetings | Belinda and Jeraldyn | Continous | In Progress
| Develop a steering committee engagement calendar and share with the ED | Jackson | TBD | In Progress
| Prioritise duty bearer engagements under outcome 2, climate justice components of the project | Sadam | Continous | Delayed/Off Track
Note: HIV awareness team was not met in Q2 reviews due to conflicting schedules

## Sheet2 (hidden)
Not Started
In Progress
Delayed/Off Track
Completed
Deferred/Cancelled