## MONTHLY PERFORMANCE
RURAL INITIATIVE FOR COMMUNITY EMPOWERMENT WEST NILE
PERIOD: THE MONTH OF….............................
MONTHLY CUMMULATIVE BUDGET PERFORMANCE
PROJECT NAME:
Code | Activity | Budget | Funds Received | Expenditures | Variance | Funds balance with the Donor | Burn Rate(against Receipt) | Absorption Rate | Comment
1.1 | Conducting Pre Project Meeting
1.1.1 |  | 400000 | 400000 | 400000 | 0 | 0 | 100% | 100%
1.1.2 |  | 2650000 | 2650000 | 2099450 | 550550 | 0 | 79.22% | 79.22%
1.1.3 |  | 100000 | 100000 | 100000 | 0 | 0 | 100% | 100%
| Sub - total | 3150000 | 3150000 | 2599450 | 550550 | 0 | 82.52% | 82.52%
2.1 | Farmer training |  |  |  | 0
2.1.1 | Training: Mobilisation | 350000 | 350000 | 300000 | 50000 | 0 | 85.71% | 85.71%
2.1.2 | Training: Lunch | 13250000 | 13250000 | 13000000 | 250000 | 0 | 98.11% | 98.11%
2.1.3 | Training: Stationery | 400000 | 400000 | 672000 | -272000 | 0 | 168% | 168%
2.1.4 | Training: Home to Home information | 4940000 | 4940000 | 4674550 | 265450 | 0 | 94.63% | 94.63%
| Sub - total | 18940000 | 18940000 | 18646550 | 293450 | 0 | 98.45% | 98.45%
3.1 | Trainer costs |  |  |  | 0
3.1.1 |  | 3750000 | 3750000 | 1877165 | 1872835 | 0 | 50.06% | 50.06%
3.1.2 |  | 2800000 | 2800000 | 1000000 | 1800000 | 0 | 35.71% | 35.71%
| Sub - total | 6550000 | 6550000 | 2877165 | 3672835 | 0 | 43.93% | 43.93%
4.1 |  |  |  |  | 0
4.1.1 |  | 1250000 | 1250000 | 800000 | 450000 | 0 | 64% | 64%
4.1.2 |  | 700000 | 700000 | 400000 | 300000 | 0 | 57.14% | 57.14%
| Sub - total | 1950000 | 1950000 | 1200000 | 750000 | 0 | 61.54% | 61.54%
5.1
5.1.1 |  | 350000 | 350000 | 350000 | 0 | 0 | 100% | 100%
5.1.2 |  | 5300000 | 5300000 | 5240000 | 60000 | 0 | 98.87% | 98.87%
5.1.3 |  | 750000 | 750000 | 810000 | -60000 | 0 | 108% | 108%
5.1.4 |  | 1400000 | 1400000 | 1400000 | 0 | 0 | 100% | 100%
| Sub - total | 7800000 | 7800000 | 7800000 | 0 | 0 | 100% | 100%
6.1
6.1.1 |  | 800000 | 800000 | 800000 | 0 | 0 | 100% | 100%
6.1.2 |  | 600000 | 300000 | 300000 | 300000 | 300000 | 50% | 50%
6.1.3 |  | 200000 | 200000 | 100000 | 100000 | 0 | 50% | 50%
| Sub - total | 1600000 | 1300000 | 1200000 | 400000 | 300000 | 75% | 75%
0
7.1 |  |  |  |  | 0
7.1.1 |  | 510000 | 510000 | 612000 | -102000 | 0 | 120% | 120%
7.1.2 |  | 750000 | 750000 | 300000 | 450000 | 0 | 40% | 40%
7.1.3 |  | 255000 | 255000 | 0 | 255000 | 0 | 0% | 0%
7.1.4 |  | 45000 | 45000 |  | 45000 | 0 | 0% | 0%
7.1.5 |  | 150000 | 150000 | 103900 | 46100 | 0 | 69.27% | 69.27%
7.1.6 |  | 1530000 | 1530000 | 1500000 | 30000 | 0 | 98.04% | 98.04%
| Sub - total | 3240000 | 3240000 | 2515900 | 724100 | 0 | 77.65% | 77.65%
8.1 |  |  |  |  | 0
8.1.1 |  | 100000 | 100000 | 100000 | 0 | 0 | 100% | 100%
8.1.2 |  | 375000 | 375000 | 375000 | 0 | 0 | 100% | 100%
8.1.3 |  | 600000 | 600000 | 612500 | -12500 | 0 | 102.1% | 102.1%
8.1.4 |  | 250000 | 250000 | 200000 | 50000 | 0 | 80% | 80%
| Sub - total | 1325000 | 1325000 | 1287500 | 37500 | 0 | 97.17% | 97.17%
9.1
9.1.1 |  | 170000 |  |  | 170000 | 170000 |  | 0%
9.1.2 |  | 100000 |  |  | 100000 | 100000 |  | 0%
9.1.3 |  | 75000 |  |  | 75000 | 75000 |  | 0%
9.1.4 |  | 15000 |  |  | 15000 | 15000 |  | 0%
9.1.5 |  | 150000 |  |  | 150000 | 150000 |  | 0%
9.1.6 |  | 510000 |  |  | 510000 | 510000 |  | 0%
| Sub - total | 1020000 | 0 | 0 | 1020000 | 1020000 |  | 0%
10.1
10.1.1 |  | 100000 |  |  | 100000 | 100000 |  | 0%
10.1.2 |  | 125000 |  |  | 125000 | 125000 |  | 0%
10.1.3 |  | 200000 |  |  | 200000 | 200000 |  | 0%
10.1.4 |  | 250000 |  |  | 250000 | 250000 |  | 0%
| Sub - total | 675000 | 0 | 0 | 675000 | 675000 |  | 0%
11.1 | Lead farmer Requirements
11.1.1 | Facilitation LF for visiting farmers 1x/month | 4114400 | 1028600 | 607550 | 421050 | 3085800 | 59.07% | 14.77%
| Sub - total | 4114400 | 1028600 | 607550 | 421050 | 3085800 | 59.07% | 14.77%
12.1 | Personnel Costs |  |  |  | 0
12.1.1 |  | 4800000 | 2400000 | 2400000 | 0 | 2400000 | 100% | 50%
12.1.2 |  | 4800000 | 2400000 | 2400000 | 0 | 2400000 | 100% | 50%
12.1.3 |  | 6000000 | 3000000 | 2500000 | 500000 | 3000000 | 83.33% | 41.67%
12.1.4 |  | 6000000 | 3000000 | 2820000 | 180000 | 3000000 | 94% | 47%
12.1.5 |  | 1800000 | 900000 | 900000 | 0 | 900000 | 100% | 50%
12.1.6 |  | 800000 | 400000 | 400000 | 0 | 400000 | 100% | 50%
| Sub - total | 24200000 | 12100000 | 11420000 | 680000 | 12100000 | 94.38% | 47.19%
13.1 | Contribution to Admin costs |  |  |  | 0
13.1.1 |  | 1320000 | 660000 | 660000 | 0 | 660000 | 100% | 50%
13.1.2 |  | 1200000 | 600000 | 600000 | 0 | 600000 | 100% | 50%
13.1.3 |  | 480000 | 240000 | 134300 | 105700 | 240000 | 55.96% | 27.98%
13.1.4 |  | 600000 | 300000 | 300000 | 0 | 300000 | 100% | 50%
| Sub - total | 3600000 | 1800000 | 1694300 | 105700 | 1800000 | 94.13% | 47.06%
14.1 | Surveys |  |  |  | 0
14.1.1 | Baseline | 1000000 | 1000000 | 784600 | 215400 | 0 | 78.46% | 78.46%
| Sub - total | 1000000 | 1000000 | 784600 | 215400 | 0 | 78.46% | 78.46%
0
| GRAND TOTAL | 79164400 | 60183600 | 52633015 | 9545585 | 18980800 | 87.45% | 66.49%